## Backlog
Story ID | Title | Description | Priority | Sprint Assigned | Comment
FRESH001 | Project Setup | As a Developer the project structure has to be created with all frameworks and plugins, So that the implementation of stories is made easier and quality assured. | High
2 | DB Design
3 | Degree Creation | As a product owner, I should be able to create a degree and able to edit the same so that I can manage the disciplines and exam cell operations | high
4 | Plug & Play | As a product owner, I should be able to bring dynamism in terms of locks, naming conventions etc. so that the dependency on the application owners is looseley coupled. | High
5 | Authentication |  | High
6 | Authorization |  | High
| Programme | As a product owner, I should be able to create a programme for a degree and manage the same. The following fields are required to manage a programme Programme Code(Eg.For P201,P202), Programme Name(Eg.Civil Engg,CSE,ECE), | Medium
S001 | Change all the course code,course name as programme code,programme name make the label names as configurable | Programme name is Civil Engineering,Computer Science Engg,ECE,Mechanical Engineering | High
S002 | In the add programme form remove start date and end date | Regulation year(Eg. 2016), Degree(Eg. BE,BTech,ME,MTech,MBA,MCA), Programme Code(Eg.For UG-U101,U102 and PG-P201,P202), Programme Name(Eg.Civil Engg,CSE,ECE), Batch year(Current academic year), Section(Eg A,B,c), Graduation(Eg UG,PG), Total year, Total Semester At the end of add programme form, have buttons to create and cancel On click of create, the values should be persisted. On Cancel, all the text values have to be cleared. On the top right have a button "Back", which on click should take the control back to programme information page/form | High |  | Implementation comp
S003 | Delete option for created programmes | Create a separate form to delete the created programmes with delete and cancel button | High |  | Not required
S004 | Rename all the subject as courses and create a course information form | In the create course creation form we should have the following fields Regulation year, batch, programme code, semester, course name, course code, paper number, paper type, subject type, course type, CIA min, CIA Max, ESE min, ESE max, Total min pass, credit points and end semester exam value mark. Paper type: Paper type should be one of the below values theory, theory with lab component, practical, Mini project, project & Viva Visa, mandatory. One item selection allowed. Subject type: Subject type is common,optional,elective,fasttrack. One item selection allowed. Course type Course type should be one of is HM,BS,ES,PC&PSC,PE,OE,project,MC,Industrial . One item selection allowed. end semester exam value mark one of ESE max, Others Others should be a text box. Once text entered, the text has to be validated to check if it is a number. (Divisible by 5 validation required or not) At the end of the form, have buttons to create and cancel On click of create, the values should be persisted. On Cancel, all the text values have to be cleared. On the top right have a button "Back", which on click should take the control back to Course information page/form | High |  | Hold
S005 | Need to create a migrate form for migration of course information depending on the same regulation year details | In the migrate form we should have the following fields Batch year, Programme code, semester, Migrate year, On submission it should list down the courses available in the batch year Each course should have the selection option (Check box at the right end) to transfer the values with edit option to change the new Course (subject) code Should have the Transfer button to migrate the values | High
S006 | Import course details option has to included | Excel file used to import the bulk course details in a single import button Sample template should be available to download | Medium
S007 | Include the parent details in the same add student form | We can have the add student form with following categories Personal Details, Academic Details, Parent Details, Current Address Details Permanent Address Details Under the Personal Detail we should have the following fields Academic year, Admission Number, Register Number, Title, First Name, Father's Name, Gender(with dropdown option), Date of Birth, Email Id, Mobile number, Aadhar number, Nationality, Religion, Caste, Admission Category(with dropdown option as Management or Counselling) Under the Academic Details we should have the following fields Batch(2016 or 2017) Degree(BE or BTech or ME or MBA) Programme(Civil or Mechanical or CSE) Section(A or B or C) Status(Regular,Lateral,Discontinue,Rejoin,Transferred) Note: While selecting the Discoutinue and Rejoin we should collect the details of Year,semester) Under the Parent Detail we should have the following fields Father's Name, Mother's Name, Mobile Number, Email ID, Annual Income Under the Current Address Details we should have the following fields Address, City, State, Country, Pincode Under the Permanent Address Details we should have the following fields Address, City, State, Country, Pincode Import option should be enabled. Should have the option to download the student details in both excel and pdf format. View and edit option has to be enabled to view the students details. | High
S008 | Retain the student status form,generate rank, bulk information form, admission category and remove the delete subject form | Add Student Status form should contain the fields Status Name(Text Box), Description(Text Box) Create and Reset button has to be present Enable the PDF and Excel download of Status details which should contain the following details Status Name, Description, Created At(Timing & Date), Created by(Admin/user), Updated At(TIming & Date), Updated by(Admin/user) ---- Generating Rank page should contain the following fields Year(Exam year), Programme code, Batch, Limit(values) On submission of values, rank certificate should get generated with pdf download option. ---- Bulk information modification form should have the fields like Programme code,batch(year) and on successful submission it should display the students details and it should be in editable format ----- In the Admission category we should be able to create the admission category in the text box. Create and Reset button has to be present Enable the PDF and Excel download of Status details which should contain the following details Status Name, Description, Created At(Timing & Date), Created by(Admin/user), Updated At(TIming & Date), Updated by(Admin/user) | High
S009 | Student Application Form to print the subject information during the time of examination | In the student Application form have the following fields Exam year, Month, Paper type, Batch, Programme code, Section, Register number from, Register number to Have the print application button and after clicking the button it should display the application details of the students | High
S010 | Create Nominal roll form | Nominal roll is of courses(subjects)which the students taken in each semester. In the nominal roll form have the following fields For the year Semester(Oct/Nov and Apr/May) Batch (2016 or 2017), Programme code(U101 or U102) On clicking the load button it should display the list of students in selected programme with the courses they are assigned in the particular semester. From Semester 2 it should display the courses taken in the particular semester and also the previous semester arrear courses(subjects) information For the elective papers have selction option and generate the nominal created. ------ Have view and modify, delete option along with pdf and excel download of nominal details ------ In the View nominal form have the following fields For the year Semester(Oct/Nov and Apr/May) Batch (2016 or 2017), Programme code(U101 or U102) After reterving the values need to have the edit option to do the changes in the nominal details | High
S011 | Retain the exam timetable form from arts college and include the dropdown option in the exam session as FN/AN. | Need to consider the even and odd semester while work on the exam timetable part. In the create exam timetable form have the following fields Year, Programme Code, Exam batch, Paper Type(Regular/Arrear), Month( Oct/Nov and Apr/May. For MBA Alone trisemester model has to be followed with following month Dec,Mar,June,Aug,Nov,Feb), Term(End/Sup), Exam Semester, Course Code(i.e Subject code), Course Name(on change after entering the Course code), Question Paper Code, Exam Date, Exam Session(FN/AN with dropdown option) In the create exam timetable have the import option | Medium
S012 | Server Backup for Arts college COE | Need to install server setup in the new machine @SKASC college and backup have to take place on daily basis. Before implementing can test the things @SKIT office
S013 | Kalpakkam - Record Management System(RMS) adding of name field in the exisiting software and solution for speed issue | Include the name field to search the records and filter records by words from the input(either pdf or image files). For speed issue finding the possiblity of submitting the comparison load timing details
S014 | Galley Arrangement to allocate the seating arrangment to students | Hall Master Screen to add the exam rooms. It should have the following fields hall name and remarks with Galley Arrangement screen should have the following fields Exam year, Examination Month(Oct/Nov, Apr/May) For MBA alone trisemester model, Term(End/Sup), Exam Date, Session, Method(Seating Count), Here enable the shuffle option and have the load, print and reset data.
S015 | Internal Mark entry option for staff members and approval option for HOD | Give the user rights to Staff members/HOD for entering the internal marks of the student. The internal mark entry form should have the following fields Batch year, Semester, Subject Code, Total internal mark with Submit and update option. Once the staff member update the marks it should display to the concern department HOD. After the approval of HOD it should get submitted to COE software
S016 | Create the absent entry form for both theory and practical exam | In the theory exam page have the following fields Hall name, Exam date, Session. On the submit it should retain the values of students those who writing exams in the particluar hall (galley arrangement)on mentioend date. In the practical exam page have the following fields Programme code, Batch, Section, Course code. | Medium
S017 | Retain the external score card from arts college |  | Low

## Sprint 2017.01
Story ID | Tasks | Estimate (In Hours) | Owner | Status | Hours Worked | Clarification Doc | Remarks
FRESH001 | Implementation | 2 | Sai | Completed | 1
| Set up in other machines | 3 | Sai | Completed | 2
| Review | 2 | Janani
2 | DB Design (User, Role, Degree, Course, Batches) | 5 | Sai | Completed | 6
| Review | 2 | Janani
3 | UI Design | 5 | Deepa
| DB Operations (search, create, update) | 5 | Deepa
| Testing | 2 | V
| Review | 4 | Janani
4 | DB Design | 3 | Sai
| DAO Implementation | 12 | Sai
| UI Design | 1 | Sai
| Caching | 4 | Sai
| Review | 4 | Janani
| Testing | 3 | V
5 | UI Design | 2 | Deepa
| DAO Implementation | 3 | Deepa
| Rule Implementation | 3 | Deepa
| Review | 1 | Janani
| Testing | 1 | V
6 | DAO Implementation | 5 | Deepa
| Code | 2 | Deepa
| Review | 2 | Janani
| Testing | 1
7 | UI Design | 5 | Deepa
| DB Operations (search, create, update) | 5 | Deepa
| Testing | 2 | V
| Review | 4 | Janani
| Code Design | 3
| Paper Type selection | 2
| Subject Type Selection | 1
| Course Type Selection | 1
| Exam Value Mark | 2
| Create Course | 6
| Testing | 6
| Total Hours | #REF!
S005 | Analysis | 2 |  |  |  | 1. Migration Form fields clarification.(Specification of Regulation year, Year of migrated batch).
| UI Design (Changes in form alignment) | 3
| Code Design | 4
| Submit Button(Ajax). | 5
| List all the courses available in the previous batch and semester | 3
| Option to select required courses for migrate | 3
| Transfer the values for migrate | 3
| Testing | 5
| Total Hours | 28
S006 | 1.Analysis | 4
| 2.Code Design | 5
| 3. Sample Excel File | 1
| 4.Excel File Imported | 5
| Total Hours | 15 |  |  |  | S007 Clarification 1. Is Dropdown is required for Gender
S007 | 1.Analysis | 4
| 2.UI Design (Changes in form alignment) | 3
| 3.Code Design | 6
| 4.Personal Details | 2.6
| 5.Academic Details | 4.6
| 6.Parent Details | 2.6
| 7.Current Address | 1.4
| 8. Permanent Address | 1.4
| 8. Create / Reset / Back | 30
| 9. Import Option | 26
| 10. PDF & EXCEL Export | 18
| 11. View / Edit | 15
| 12. Delete (Student Record will be Deleted from each and everywhere) | 20
| Total Hours | 134.6
S008 | 1. Analysis | 3
| 2. Code Design | 4
| 3. Add Student Status & Create and Reset button | 1
| 4. Enable the PDF and Excel | 1
| 6. Generating Rank(Will be considered after mark entry) | 16
| 7. Bulk information modification(After Student Created) | 10
| 8. Admission category & Create and Reset Button | 1.3
| 9. Enable the PDF and Excel | 1
| Total Hours | 37.3
S009 | 1.Analysis | 4
| 2.UI Design (Changes in form alignment) | 3
| 3.Code Design | 4
| 4.Student Application Form | 16 |  |  |  | 1. Need to discuss about the Application Form 2. Do you required New Curriculam Information Form 3. IF YES (Field Information) 4. If No (Subject Pricings will be Hardcoded in the Application Form)

## Sheet3
Deepa | 55
Sai | 55